## Sheet1
Task | Start date | Duration | 2023-03-01 | 2023-03-02 | 2023-03-03 | 2023-03-04 | 2023-03-05 | 2023-03-06 | 2023-03-07 | 2023-03-08 | 2023-03-09 | 2023-03-10 | 2023-03-11 | 2023-03-12 | 2023-03-13 | 2023-03-14 | 2023-03-15 | 2023-03-16 | 2023-03-17 | 2023-03-18 | 2023-03-19 | 2023-03-20 | 2023-03-21 | 2023-03-22 | 2023-03-23 | 2023-03-24 | 2023-03-25 | 2023-03-26 | 2023-03-27 | 2023-03-28 | 2023-03-29 | 2023-03-30 | 2023-03-31 | 2023-04-01 | 2023-04-02 | 2023-04-03 | 2023-04-04 | 2023-04-05 | 2023-04-06 | 2023-04-07 | 2023-04-08 | 2023-04-09 | 2023-04-10 | 2023-04-11 | 2023-04-12 | 2023-04-13 | 2023-04-14 | 2023-04-15 | 2023-04-16 | 2023-04-17 | 2023-04-18 | 2023-04-19 | 2023-04-20 | 2023-04-21 | 2023-04-22 | 2023-04-23 | 2023-04-24 | 2023-04-25 | 2023-04-26 | 2023-04-27 | 2023-04-28 | 2023-04-29 | 2023-04-30
Project plan & set up environment | 2023-03-01 | 6
Start activity report & software architecture | 2023-03-07 | 13
Login, log out, sign up code & doc | 2023-03-07 | 13
Homepage with data from database | 2023-03-20 | 7
Testing plan and test existing functions | 2023-03-20 | 7
Doc & implementation to manage products(ad) | 2023-03-20 | 7
Doc, code and test manage user profile | 2023-03-27 | 7
Doc, code and test product sorting | 2023-03-27 | 7
Doc, code and test add to shopping cart | 2023-03-27 | 7
Doc, code and test make order | 2023-04-03 | 7
Doc, code and test view & manage order(ad) | 2023-04-03 | 7
Doc, code and test apply voucher | 2023-04-10 | 7
Doc, code and test mange voucher(ad) | 2023-04-10 | 7
Doc, code and test online payment | 2023-04-17 | 7
Review all codes and docs | 2023-04-24 | 7
Add search functions if enough time | 2023-04-24 | 7